## Website Migration SEO
Website Migration SEO Checklist
Who it is for: SEOs, developers, migration project leads ¦ Page: /checklists/website-migration-seo-checklist/ ¦ Edit light yellow cells only
ID | Section | Check | What to Verify | Priority | Status | Owner | Date Checked | Notes | Section Page URL
Pre-Migration Crawl
WMS-001 | Pre-Migration Crawl | Crawl the old site | Full URL inventory with status, titles and canonicals saved | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/pre-migration-crawl/
WMS-002 | Pre-Migration Crawl | Export top pages | Top pages by traffic and backlinks are listed | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/pre-migration-crawl/
URL Mapping
WMS-003 | URL Mapping | Map old to new URLs | Every old URL has a one to one destination | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/url-mapping/
Redirect Plan
WMS-004 | Redirect Plan | Build redirect rules | 301 rules cover all mapped URLs without chains | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/redirect-plan/
Canonicals
WMS-005 | Canonicals | Update canonicals | Canonicals point to new URLs | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/canonicals/
Internal Links
WMS-006 | Internal Links | Update internal links | Internal links point directly to new URLs | Medium | Not started |  |  |  | /checklists/website-migration-seo-checklist/internal-links/
XML Sitemap
WMS-007 | XML Sitemap | Prepare new sitemap | New sitemap lists new canonical URLs | Medium | Not started |  |  |  | /checklists/website-migration-seo-checklist/xml-sitemap/
Robots.txt
WMS-008 | Robots.txt | Prepare production robots.txt | No staging blocks carried over | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/robotstxt/
Metadata
WMS-009 | Metadata | Preserve metadata | Titles and descriptions of top pages are carried over or improved | Medium | Not started |  |  |  | /checklists/website-migration-seo-checklist/metadata/
Structured Data
WMS-010 | Structured Data | Preserve schema | Schema types are retained on new templates | Medium | Not started |  |  |  | /checklists/website-migration-seo-checklist/structured-data/
Analytics
WMS-011 | Analytics | Migrate tracking | Analytics and conversions track on the new site | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/analytics/
Staging Validation
WMS-012 | Staging Validation | Crawl staging | Staging crawl matches the URL map | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/staging-validation/
Launch Day
WMS-013 | Launch Day | Deploy redirects | Sample old URLs return 301 to correct pages | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/launch-day/
WMS-014 | Launch Day | Submit sitemaps | New sitemap submitted in Search Console | Medium | Not started |  |  |  | /checklists/website-migration-seo-checklist/launch-day/
Post-Migration Crawl
WMS-015 | Post-Migration Crawl | Crawl old URL list | Every old URL returns a single 301 to a 200 | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/post-migration-crawl/
WMS-016 | Post-Migration Crawl | Crawl new site | No new 4xx, noindex or canonical errors | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/post-migration-crawl/
Compare Old vs New
WMS-017 | Compare Old vs New | Compare crawls | Titles, canonicals and indexability match expectations | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/compare-old-vs-new/
Monitor
WMS-018 | Monitor | Monitor traffic and indexing | Organic traffic and indexed pages tracked daily for 4 weeks | High | Not started |  |  |  | /checklists/website-migration-seo-checklist/monitor/

## How to Use
SiteAuditLint SEO Checklist Library
How to use this workbook
1. Each tab is one checklist. Each Section in a tab becomes its own page at /checklists/<checklist>/<section>/.
2. Fill in only the light yellow cells: Status, Owner, Date Checked, Notes.
3. Status values: Not started, Pass, Fail, Fixed, Verified, N/A. Pick from the dropdown.
4. Workflow: Check, mark Pass or Fail, fix, mark Fixed, re-crawl, mark Verified.
5. The Overview tab calculates progress automatically from every checklist tab.
6. The Page Map tab lists every section page with its URL slug and download formats (PDF, XLSX, DOCX, Print).
Example row (Technical SEO, row 2): Status = Fail, Owner = Dev team, Notes = 14 URLs in a 3 hop chain from /old-blog/.
Run the same checks automatically with SiteAuditLint: Crawl, Find, Fix, Re-crawl, Compare, Monitor.